## Slide 1: Welcome!
We’re glad you’re here.
INCOSE Enchantment Chapter Monthly Meeting

## Slide 2: We respectfully request:
Mute your audio when you are not speaking
*6 toggle or in GlobalMeet left-side, your name
Discussion and questions are encouraged!
Put questions in the chat box or unmute yourself to speak up.

## Slide 3: Meeting Materials
Slide presentations can be downloaded prior to start of the meeting from the Meeting Materials page of our website:
https://www.incose.org/incose-member-resources/chapters-groups/ChapterSites/enchantment/resources/meeting-materials
If recording is authorized by speaker, the video will be posted at the link above within 24 hours.

## Slide 4: SEP Training
CSEP Courses by Certification Training International:
  CTI currently is offering online course offerings, see
  https://certificationtraining-int.com/incose-sep-exam-prep-course/
  Our chapter has two SEP mentors:
  Ann Hodges alhodge@sandia.gov
  Heidi Hahn drsquirt@outlook.com

## Slide 5: Upcoming meetings
September 8, 2021: Brian Kennedy, Leveraging Set-Based Practices to Enable Efficient Concurrency in Large Systems and Systems-of-Systems Engineering
October 13, 2021: Jim Armstrong – “Kitchens”
November 10, 2021: Jennifer Russell – “Smart Cities” (tentative)

## Slide 6: Introductions
Please type your name, position, and organization in the Chat window
Photo by Adam Solomon on Unsplash

## Slide 7: Survey
The link for the online survey for this meeting is
www.surveymonkey.com/r/2021_08_MeetingEval
Your feedback is important!

## Slide 8: Enchantment Chapter Monthly Meeting
WBS Integration with an Effective Schedule
Abstract: This presentation addresses the following questions:
How a WBS fits into the big picture of planning and managing a project
Why the WBS should form the foundation for project schedule development and elaboration
The hierarchical structure of a WBS
WBS nodes vs. project activities
Managing and relating WBS data within a project schedule
Download recording from the Library at www.incose.org/enchantment
NOTE: This meeting will be recorded

## Slide 9: Speaker Bio
Patrick Foley is a highly experienced project controls data specialist who has built and supervised the deployment of complex project data management platforms. His business and technical qualifications span more than 30 years. He is employed by PM Tec Inc. and currently on contract to Sandia Laboratories. As a scheduling expert he has functioned as a team lead, team member, and subject matter expert in schedule controls for projects requiring broad institutional implementation as well as projects requiring detailed unit operation process improvement. He is a scheduling expert in both Microsoft Project and Primavera P6. He is also an accomplished VBA code writer and database designer/engineer. As an active volunteer with the local PMI (Rio Grande) Chapter, he has delivered PMP prep course material for the chapter and conducted scheduler boot camp training at Sandia Labs.
Mr. Foley is a certified Project Management Professional (PMP) and holds an M.A. in Information and Communication Studies from California State University and a B.S. in International Business from the University of Colorado, Boulder.

## Slide 10: The Work Breakdown Structure or “WBS”
Patrick Foley
8/11/2021

## Slide 11: Topic Organization
WBS Defined
Organization of the WBS
WBS as a Scope Statement
Detail activities as they relate to the WBS
WBS in the context of a project and activity derivation
Numbering the WBS
The PWBS & CWBS
WBS is an attribute in a schedule database
WBS as it relates to Earned Value

## Slide 12: The WORK in the Work Breakdown Structure (WBS)
1
Pyramid
The WBS is a parcel containing descriptors of ALL of the WORK required to execute a specific project.
12
Notes: Time: 1 min
Emphasize: difference between WBS and network/schedule
Detail tasks should NOT be in the WBS,
If they are, they would be found at the “atomic” or lowest level within a branch of the WBS
Remove them to the schedule if you can

## Slide 13: WBS is “Broken Down”
1
Pyramid
1.1
Foundation
1.2
Walls
1.4
Treasure
1.3
Burial Chamber
WBS is broken down into a collection of smaller, manageable parcels
Enables the organization of work, resource assignment and costs
Parcels are usually organized by component.
13
Notes: Time: 1 min
Emphasize: difference between WBS and network/schedule
Detail tasks should NOT be in the WBS,
If they are, they would be found at the “atomic” or lowest level within a branch of the WBS
Remove them to the schedule if you can

## Slide 14: Work Breakdown Structures (WBS) - Graphically
The WBS is a hierarchical breakdown of project effort into lower level units of work (e.g. Work Packages) by deliverable product, existing procedures or process, etc.
There is NO precedence logic or durations within the WBS. It is NOT a logical network/schedule.
It represents the foundation of the Earned Value Management environment (Cost/Control Accounts) AND the “parents” of schedule activities.
1
Pyramid
1.1
Foundation
1.2
Walls
1.4
Treasure
1.3
Burial
Chamber
1.1.1
Survey
1.1.2
Leveling
1.1.3
Grading
1.2.1
North Wall
1.2.2
South Wall
1.2.3
East Wall
1.2.4
West Wall
1.3.1
Pharaoh
1.3.2
Pharaohess Chamber
1.4.1
Floor
1.4.2
Ceiling
1.4.3
Walls
1.2.2.1
Secret
Entrance
1.2.2.2
Trap Door
1.2.4.1
Entrance
1.2.4.2
Booby Trap
1.2.4.3
Arming Mechan.
1.3.1.1
Floor
1.3.1.2
Ceiling
1.3.1.3
Walls
1.3.2.1
Floor
1.3.2.2
Ceiling
1.3.2.3
Walls
1.3.1.3.1
Entrance
1.3.2.3.1
Entrance
1.4.3.1
Secret
Entrance
1.4.3.1
Entrance
1.4.3.2
Booby Trap
1.4.3.3
Arming Mechan.
14
Notes: Time: 2 min
The WBS is NOT a network!

## Slide 15
GOOD,
FAST or CHEAP?
SCOPE
SCHEDULE
RESOURCES
Changes to one will affect the others.
You can only optimize two at a time!
WBS in the “Triple Constraint” of Project Management
15
The WBS chart is a GRAPHICAL DEPICTION of a project scope statement
Modifications to the WBS are likely to impact SCHEDULE and/or RESOURCE requirements
This Photo by Unknown Author is licensed under CC BY-SA-NC

## Slide 16: Basic Schedule development/elaboration
Develop Project Work Breakdown Structure (WBS)
Decompose WBS into activity list
Determine Activity Precedence
Estimate activity durations
Assign Resources
WBS
Activity List
Activity
Precedence
Duration
Estimates
Assign Resources
16
Notes: Time: 2 min
Once you have ACTIVITIES, MILESTONES, PRECEDENCE and DURATIONS you have a basic schedule and it begins to take on a life of its own.
The process is rarely this “clean”, just do your best to keep the ideal process in mind

## Slide 17: WBS Within the Big Picture of a Project
17
Notes: Time: 1 min
This is a highly DETAILED conceptual project flow;
Emphasize the schedule development and schedule management elements

## Slide 18: Numbering the WBS
1
Pyramid
1.1
Foundation
1.2
Walls
1.4
Treasure Chamber
1.3
Burial
Chamber
1.1.1
Survey
1.1.2
Leveling
1.1.3
Grading
1.2.1
North Wall
1.2.2
South Wall
1.2.3
East Wall
1.2.4
West Wall
1.3.1
Pharaoh
1.3.2
Pharaohess Chamber
1.4.1
Floor
1.4.2
Ceiling
1.4.3
Walls
1.2.2.1
Secret
Entrance
1.2.2.2
Trap Door
1.2.4.1
Entrance
1.2.4.2
Booby Trap
1.2.4.3
Arming Mechan.
1.3.1.1
Floor
1.3.1.2
Ceiling
1.3.1.3
Walls
1.3.2.1
Floor
1.3.2.2
Ceiling
1.3.2.3
Walls
1.3.1.3.1
Entrance
1.3.1.3.2
Booby Trap
1.3.2.3.1
Entrance
1.3.2.3.2
Booby Trap
1.4.3.1
Secret
Entrance
1.4.3.1
Entrance
1.4.3.2
Booby Trap
1.4.3.3
Arming Mechan.
While there is no specific rule on what type of numbering system to use in a WBS, the pharaoh’s manager chose to use a simple hierarchical numbering system on each node
You may have organizational standards or requirements for numbering your WBS (i.e. DOD is “MIL-STD-881C”)
18

## Slide 19: Control Accounts & Work Packages in the WBS
Lowest Level Nodes in the WBS = Work Packages
Nodes just above Work Packages = Control Accounts
1
Pyramid
1.1
Foundation
1.2
Walls
1.4
Treasure
1.3
Burial
Chamber
1.1.1
Survey
1.1.2
Leveling
1.1.3
Grading
1.2.1
North Wall
1.2.2
South Wall
1.2.3
East Wall
1.2.4
West Wall
1.3.1
Pharaoh
1.3.2
Pharaohess Chamber
1.4.1
Floor
1.4.2
Ceiling
1.4.3
Walls
1.2.2.1
Secret
Entrance
1.2.2.2
Trap Door
1.2.4.1
Entrance
1.2.4.2
Booby Trap
1.2.4.3
Arming Mechan.
1.3.1.1
Floor
1.3.1.2
Ceiling
1.3.1.3
Walls
1.3.2.1
Floor
1.3.2.2
Ceiling
1.3.2.3
Walls
1.3.1.3.1
Entrance
1.3.2.3.1
Entrance
1.4.3.1
Secret
Entrance
1.4.3.1
Entrance
1.4.3.2
Booby Trap
1.4.3.3
Arming Mechan.
19
Notes: Time: 2 min
The WBS is NOT a network!

## Slide 20: Detail Activities as they relate to the WBS
Lowest-level WBS containers (Work Packages) are broken down into schedule activities. Detail activities in a project schedule represent a DECOMPOSITION of the lowest level nodes in the WBS into specific activities.
1.1.1
Survey
1.1.2
Leveling
Hire Surveyor
Calibrate
Measure
Record
Stake out
Rake down
Water down
1
Pyramid
1.1
Foundation
1.2
Walls
1.4
Treasure
1.3
Burial
Chamber
The LEVELING “Work Package”
The SURVEY “Work Package”
If an activity cannot be found in the WBS, it should not be in your schedule
20
Notes: Time: 2 min
Emphasize: difference between WBS and network/schedule
Detail tasks should NOT be in the WBS,
If they are, they would be found at the “atomic” or lowest level within a branch of the WBS
Remove them to the schedule if you can

## Slide 21: WBS / PWBS / CWBS
1
Pyramid
1.1
Foundation
1.2
Walls
1.4
Treasure Chamber
1.3
Burial
Chamber
1.1.1
Survey
1.1.2
Leveling
1.1.3
Grading
1.2.1
North Wall
1.2.2
South Wall
1.2.3
East Wall
1.2.4
West Wall
1.3.1
Pharaoh
1.3.2
Pharaohess Chamber
1.4.1
Floor
1.4.2
Ceiling
1.4.3
Walls
1.2.2.1
Secret
Entrance
1.2.2.2
Trap Door
1.2.4.1
Entrance
1.2.4.2
Booby Trap
1.2.4.3
Arming Mechan.
1.3.1.1
Floor
1.3.1.2
Ceiling
1.3.1.3
Walls
1.3.2.1
Floor
1.3.2.2
Ceiling
1.3.2.3
Walls
1.3.1.3.1
Entrance
1.3.1.3.2
Booby Trap
1.3.2.3.1
Entrance
1.3.2.3.2
Booby Trap
1.4.3.1
Secret
Entrance
1.4.3.1
Entrance
1.4.3.2
Booby Trap
1.4.3.3
Arming Mechan.
WBS = Work Breakdown Structure
  PWBS = Program Work Breakdown Structure
  CWBS = Contract Work Breakdown Structure (> Level 3)
21
PWBS
CWBS

## Slide 22: A Project Schedule is a Database
Schedule management programs are databases having tables, records and fields integrated with an elegant calculator
The WBS FIELD is one of numerous attributes in a table of your activities
This Photo by Unknown Author is licensed under CC BY-SA
TABLE
RECORD
FIELD / Attribute
22
Notes: Time: 3 min

## Slide 23: WBS in the Context of Earned Value Management
WBS Work Breakdown Structure
OBS Organization Breakdown Structure
BAC Budget at Complete
PV Planned Value (BCWS)
EV Earned Value (BCWP)
AC Actual Cost (ACWP)
Formulas
Basic Terms
CPI Cost Performance Index (EV/AC)
CV Cost Variance (EV - AC)
SPI Schedule Performance Index (EV/PV)
SV Schedule Variance (EV - PV)
TCPI To Complete Performance Index (BAC-EV)/(BAC-AC)
ETC Estimate to Complete (EAC - AC)
EAC Estimate at Complete (BAC/CPI)
IEAC Independent EAC (various)
VAC Variance at Complete (BAC – EAC)
23

## Slide 24: WBS in the Context of Earned Value Management
24

## Slide 25
This Photo by Unknown Author is licensed under CC BY
Questions
?
+
+
+
25
Notes: Time: 10 min