## Issues Log
Issue Log <Chapter>
Initiative
Issue No. | Team/ Originator | Registration Date | Priority | Issue Description | Assigned to | Due Date | Actual Date | Status | Comment/Status
1 | Enter project name and customer name
2 | Enter Action information from Minutes, status report or any other source
Note on A3: : Assign a unique number to the issue.
Note on B3: : Where does the issue come from? Who has raised the issue?
Note on C3: : At what date was the issue raised?
Note on D3: : L = Low M = Medium H = High
Note on E3: : Enter a short but telling description, what the issue is about and what possible solutions are discuesssed
Note on F3: : Enter name of person responsible for solving issue
Note on G3: : Enter date until when the issue needs to be solved.
Note on H3: : Enter date when issue was solved.
Note on I3: : R = Registered I = In discussion S = Solved

## Nov 19, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-11-19 | B |  | Action | Documentation | Should a new customer be created when a customer buys direct from ETS when a previous distributor customer | Wade | 2002-11-19
2002-11-19 | B |  | Action | Documentation | IT to print out what the order review process checks | Rebecca | 2002-11-19
2002-11-19 | B |  | Gap | Requirement | Need ownership field for OL24. |  |  |  | OL24 is currently a leadsource and it should not be a leadsource it should just show ownership
2002-11-19 | B |  | Gap | Requirement | Ability to track all originating marketing sources |  |  |  | Conversion issue
2002-11-19 | B |  | Gap | Requirement | System should allow for SIC code field |  |  |  | Field should not be mandatory
2002-11-19 | B |  | Gap | Requirement | Ability to reactivate a customer that was previously deactivated
2002-11-19 | B |  | Gap | Requirement | Any marketing address that does not have a zip + 4 is to go into a que for Advertising to look at and correct
2002-11-19 | B |  | Gap | Requirement | Ability to identify and alert duplicate ship to addresses and allow rep to look at original |  |  |  | This check should include Marketing, Bill to and Ship to
11/'19/02 | B |  | Gap | Requirement | Ability to add a "Deliver To" address |  |  |  | "Deliver To" address will be used for Distributor accts.
2002-11-19 | B |  | Action | Documentation | Get the business rules for defining duplicate addresses | Detra | 2002-11-19
2002-11-19 | B |  | Gap | Requirement | Returned email addresses should go into a que for someone to look at and resolve
2002-11-19 | B |  | Gap | Requirement | Ability for Sales Manager to view lead extensions by rep and ability to re-assign
2002-11-19 | B |  | Gap | Requirement | Abillity to send an alert to a Sales Manager if a customer group changes |  |  |  | For example, if an attribute changes from a large salon to a small salon or commemrcial to residential. This may be for Data Cop
2002-11-19 | B |  | Gap | Requirement | When a Residential lead is re-assigned it does not remove from post card mailing
2002-11-19 | B |  | Gap | Requirement | Ability for system to create a note if anything is changed in the sales opportunity
2002-11-19 | B |  | Action | Documentation | Aston to make a recommendation on Business Rule 3A |  |  |  | Can departments have different expire dates
2002-11-19 | B |  | Gap | Requirement | System to provide questionnaire based on order line item
2002-11-19 | B |  | Gap | Requirement | Create a payment module that applies warranty as a payment type
2002-11-19 | B |  | Gap | Requirement | Ability to print coupon on invoices based on current promotions |  |  |  | Marketing will determine what orders should receive a coupon
2002-11-19 | B |  | Gap | Requirement | Ability to see available promotions for customers
2002-11-19 | B |  | Gap | Requirement | Ability to automatically apply promotion or rebate to sales order
2002-11-19 | B |  | Gap | Requirement | Ability to capture Referral information
2002-11-19 | B |  | Decision | Documentation | Define business rules to pay referrals |  |  |  | How will information be validated? What will time frame be? |  | N
2002-11-19 | B |  | Decision | Documentation | Should referral amount adjust sales rep commission? | [5 empty] | Y
2002-11-19 | B |  | Gap | Requirement | Ability to identify referral customers |  |  |  | We currently use a blue ribbon
2002-11-19 | B |  | Action | Documentation | Add blue ribbon referrals to UCDB document | Mike Alonzi
2002-11-19 | B |  | Gap | Requirement | Ability for sales reps to locate referrals
2002-11-19 | B |  | Gap | Requirement | Ability to apply terms per line item |  |  |  | This will allow AG, SB, and CG to be on the same order

## Oct. 22, 2002 (hidden)
ETS Issue Log | [7 empty] | Status | Description | Total
[8 empty] | 1 | Open | 7
[8 empty] | 2 | In Development - Aston | 0
[8 empty] | 3 | Resolved - Aston | 0
[8 empty] | 4 | In Test - ETS | 0
[8 empty] | 5 | Approved - ETS | 0
[8 empty] | 6 | Deferred | 0
[8 empty] | 7 | No Action | 0
Date
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-10-22 | B | 1 | Issue |  | Search field from Open Step to Axapta |  |  |  | We currently have the ability to search all scratchpad fields independently from each other. Search is based on an or statement not a filter. Filter applies to Axapta | 1 | N
2002-10-22 | B | 2 | Issue |  | Customer account # changes when converted from prospect to customer |  |  |  | Once a customer is created in the system, keep the same customer account number the same | 1 | N
2002-10-22 | B | 3 | Issue |  | Notes fields |  |  |  | Too many fields for notes. Potential for some to get missed | 1
2002-10-22 | B | 4 | Issue |  | There is no record of emails sent out |  |  |  | We currently log an interaction when an email is sent to customer. Axapta does not record that | 1
2002-10-22 | B | 5 | Issue |  | Address site use is not easily specified |  |  |  | Addresses are not easily labeled marketing, bill to or ship to. Addresses are currently mandatory in Open Step | 1
2002-10-22 | B | 6 | Issue |  | How are referrals paid |  |  |  | Would like for referrals to be paid automatically. Sales rep decides dollar amount. AR can either cut a check or issue a credit. Referral is not paid until unit is shipped | 1
2002-10-22 | B | 7 | Issue |  | OL24'S |  |  |  | This is a policy issue. Will OL24's exist in Axapta. Need a way to have joint ownership of an account | 1
2002-10-22 | B | 8 | Issue |  | Cannot select customer class (commercial or residential)
2002-10-22 | B | 9 | Issue |  | Main contact can be changed when creating a record
2002-10-22 | B | 10 | Security |  | Sales reps can see all Activities for all reps | Rebecca
2002-10-22 | B | 11 | Issue |  | Putting multiple addresses on orders (bill to & ship to) |  |  |  | Address fields should be mandatory on quotes and sales orders. Should be able to see bill to and ship to address on quotes and sales orders.
2002-10-22 | B | 12 | Issue |  | Adding an active date range to view campaigns
2002-10-22 | B | 13 | Action |  | Calculating freight & sales tax in a Quotation | Erik Stromblad | 2002-10-29
2002-10-22 | B | 14 | Issue |  | Apply credit card payments to sales order (single or multiple) |  |  |  | Axapta does not allow a credit card to be authorized. Customer may pay with several credit cards or payment options
2002-10-22 | B | 15 | Issue |  | Making Address mandatory when creating new customers/prospects
2002-10-22 | B | 16 | Change |  | Can Encyclopedia button link to intranet site
2002-10-22 | B | 17 |  |  | Financials Tab |  |  |  | Currently shows totals for last year vs. this year. Can this be changed to separate Products and Equipment.
2002-10-22 | B | 18 | Issue |  | Putting a contact name in Quotation |  |  |  | Should be a mandatory field

## Oct. 23, 2002 (hidden)
ETS Issue Log
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-10-23 | B | 19 | Change |  | Automatic notification to a Products rep that a customer has bought a bed or notification to Equipment that a salon has purchased lotion and there is currently no current lead
2002-10-23 | B | 20 | Issue |  | Key line for return mail (Detra)
2002-10-23 | B | 21 | Action |  | Print out Strata budget | Detra
2002-10-23 | B | 22 | Issue |  | Adding multiple phone numbers for one customer account
2002-10-23 | B | 23 | Change |  | Using Suspects status |  |  |  | Detra purchases lists of names of people that have not shown previous interest.
2002-10-23 | B | 24 | Action |  | Get user manual for team | Mike Alonzi |  |  |  | 1 | Y
2002-10-23 | B | 25 | Issue |  | Using multiple payment types
2002-10-23 | B | 26 | Issue |  | Importing Strata data into Axapta |  |  |  | Use for campaigns
2002-10-23 | B | 27 | Action |  | Do not email list | Dan Schaffer |  |  | When an automatic email is sent out, customer may want to select to no longer receive marketing email. Will this work for Axapta

## Oct. 24, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-10-24 | B | 28 | Issue |  | No internal or external notes on quotations or sales orders |  |  |  | internal notes are used to support why an order was placed (no charge, warranty status, bed type, etc) external notes are used to provide instructions to the driver
2002-10-24 | B | 29 | Issue |  | Gift order type |  |  |  | Is there a way to delay an invoice from being shipped out if bed was purchased as a gift
2002-10-24 | B | 30 | Issue |  | Service Requests |  |  |  | Is there a place to record customer complaints?
2002-10-24 | B | 31 | Issue |  | Block sales commissions |  |  |  | Axapta shows sales commissions based off of a percentage. ETS pays off of blocks or $50 per $1000 sold
2002-10-24 | B | 32 | Change |  | Automatic questionnaire for bed shipments |  |  |  | Send questionnaire based on ship date for first time buyer only
2002-10-24 | B | 33 | Issue |  | Deactivate contact information |  |  |  | If a contact is no longer active on an account, do let the sales reps see them at all
2002-10-24 | B | 34 |  |  | Separate area code and phone number into two different fields
2002-10-24 | B | 35 | Issue
2002-10-24 | B | 36 | Action |  | Check CTI compatibility | Erik Stromblad
2002-10-24 | B | 37 | Action |  | Look at upgraded CTI for compatibility | Charity Mitchell |  |  | Ability to see advertising source when customer zeros out or call is transferred internally. What date will this be done
2002-10-24 | B | 38 | Issue |  | No field exists for lead source (sales opportunity)
2002-10-24 | B | 39 | Action |  | Need clarification on definitions page of OMS documentation | Mike Alonzi
2002-10-24 | B | 40 | Issue |  | Need to create finance apps
2002-10-24 | B | 41 | Issue |  | Cancel button to opt of sending automatic email

## Oct. 29, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-10-29 | B | 42 | Issue | Cross Function | Certain settings should be defined for prospects | Team B |  |  | Handout is Settings on customer table regardless of business relation setup
2002-10-29 | B | 43 | Issue | Cross Function | No price list is attached to a customer or prospect
2002-10-29 | B | 44 | Issue | Cross Function | Ability to track referrals |  |  |  | Track who is being paid for referrals (vendors & customers)
2002-10-29 | B | 45 | Action | Cross Function | Clarify Process 14 Original super process 3 | Team B |  |  | "Ability to allow referral and other advertising/promotion codes to maybe trigger follow-up workflow"
2002-10-29 | B | 46 | Issue | Cross Function | Exempt or non-exempt status of customer should follow each ship to address on customers order
2002-10-29 | B | 47 | Issue | Cross Function | Ability to add several ship to addresses on one order |  |  |  | Several drop ship addresses for distributors
2002-10-29 | B | 48 | Issue | Cross Function | Make leasing company address available for all finance customers |  |  |  | Possible resolution is make Leasing Company a customer and link address to finance customer in Invoice Account field
2002-10-29 | B | 49 | Action | Cross Function | Look at the definition of Customer | Team B |  |  | Current definition says that a prospect is not a customer until item is shipped. May need to change definition to money received
2002-10-29 | B | 50 | Issue | Cross Function | Convert customer back to prospect if money doesn’t come in
2002-10-29 | B | 51 | Issue | Cross Function | Separating products and equipment customers |  |  |  | creating two customers vs. one
2002-10-29 | B | 52 | Issue | Cross Function | Orders should not be available for the warehouse to ship until money is applied
2002-10-29 | B | 53 | Decision |  | Define when a prospect is converted to a customer | Ann Trainer
2002-10-29 | B | 54 | Decision |  | Define when a quote is converted to a sales order | Ann Trainer
2002-10-29 | B | 55 | Change |  | Show current ownership of lead

## Oct. 30, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-10-30 | B | 56 | Issue |  | Track leads that are not being worked
2002-10-30 | B | 57 | Issue |  | Ability to see multiple opportunities for each customer
2002-10-30 | B | 58 | Issue |  | Too many steps
2002-10-30 | B | 59 | Issue |  | Must have a quote to have a sales opportunity |  |  |  | Sales rep may talk to customer and send a catalog before the customer knows exactly what they want to buy
2002-10-30 | B | 60 | Issue |  | Internet Leads
2002-10-30 | B | 61 | Issue |  | Validate all addresses against USPS to make sure address is deliverable
2002-10-30 | B | 62 | Decision |  | How are non-deliverable addresses handled |  |  |  | Suggestions: flag address as not validated or not allow in system
2002-10-30 | B | 63 | Decision |  | Validate non-US addresses
2002-10-30 | B | 64 | Issue |  | Link caller area code to promo code for reporting
2002-10-30 | B | 65 | Issue |  | Initiate workflow to merge duplicate addresses when a new customer is created or during a search for existing customers
2002-10-30 | B | 66 | Issue |  | Ability to merge duplicate accounts
2002-10-30 | B | 67 | Decision |  | Who should be able to merge accounts |  |  |  | One person will merge accounts
2002-10-30 | B | 68 | Issue |  | Ability to have customer/distributor account forms track distributor contract status. For distributors without current contracts, system prevents orders from being placed
2002-10-30 | B | 69 | Issue |  | Price list and promo code changes are not logged when overwritten
2002-10-30 | B | 70 | Issue |  | Being able to import mapics bom from spectrum and maintaining boms in Axapta
2002-10-30 | B | 71 | Decision |  | How are quotes going to be recalculated if freight changes or to add sales tax |  |  |  | Add disclaimer to customer to notify of possible changes
2002-10-30 | B | 72 | Action |  | Ask Jen if Warranty module will support process 18 | Erik Stromblad |  |  | Process states: "ability to access warranty information during order entry (e.g. warranty programs available for each model)
2002-10-30 | B | 73 | Issue |  | Allow reps to change commission splits on sales orders
2002-10-30 | B | 74 | Issue |  | Accurate reporting on splits
2002-10-30 | B | 75 | Issue |  | Ability for payroll to pay commissions based on sales order splits
2002-10-30 | B | 76 | Decision |  | Who can sell what products |  |  |  | Process 18 "ability to select any type of product to order lamps, lotions, equipment, etc. to promote cross selling
2002-10-30 | B | 77 | Issue |  | Automatically calculate or update and display sales commissions as items are added to the order
2002-10-30 | B | 78 | Decision |  | How will marketing and product information on competitors be formatted (Encyclopedia?)
2002-10-30 | B | 79 | Gap |  | Ability to automate level and goal status calculation, making this status visible |  |  |  | Some levels are calculated by item
2002-10-30 | B | 80 | Decision |  | Should groups be able to complete another reps partial orders |  |  |  | for example, if an equipment rep is out of the office, should another equipment rep be able to open a partial order and complete it for the rep
2002-10-30 | B | 81 | Definition |  | How do order types work in Axapta
2002-10-30 | B | 82 | Definition |  | Need definition on process number 18 |  |  |  | Process states: "Ability to deselect line items (pull freight or subtotal calculations) without deleting them from the draft
2002-10-30 | B | 83 | Gap |  | Ability to provide an alert when a draft is "aging". After some time it should be purged from the system

## Oct. 31, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-10-31 | B | 84 | Gap |  | Ability to map, analyze & review salon/distributor field trip & Florida direct store delivery (DSD) travel routes, and track field training by geography and demographics
2002-10-31 | B | 85 | Gap |  | Automatically schedule an activity or callback
2002-10-31 | B | 86 | OMS |  | Add Priority, Grade, Scheduling Callbacks, and Customer Group (commercial or residential) |  |  |  | Page 21 of OMS document under New Prospect Creation version 1.0
2002-10-31 | B | 87 | Gap |  | Ability to send collateral
2002-10-31 | B | s | Security |  | Prospect/customer classification | Rebecca
2002-10-31 | B | 89 | Action |  | Add Security Issues to all log sheets | Rebecca
2002-10-31 | B | 90 | Gap |  | Make Distributor customer group available but do not allow a sales order to be created without contract
2002-10-31 | B | 91 | Decision |  | Who will be able to deactivate customer records/contacts/addresses, etc
2002-10-31 | B | 92 | Decision |  | What are the rules to deactivate an account
2002-10-31 | B | 93 | Action |  | Define "Deactivate" | Team B
2002-10-31 | B | 94 | Gap |  | Axapta does not have ability to deactivates
2002-10-31 | B | 95 | Gap |  | Route calls to specific rep based on current sales opportunity instead of queue |  |  |  | Should be handled by Team E
2002-10-31 | B | 96 | Gap |  | Name and extension of sales rep with current sales opportunity should display on caller id
2002-10-31 | B | 97 | OMS |  | There should be a step added before create new prospect to search for existing prospect |  |  |  | Page 14 OMS System Requirements in work flow version 1.0
2002-10-31 | B | 98 | Gap |  | Ability to see finance information in business relationship table
2002-10-31 | B | 99 | Action |  | Give Erik all the information that should be seen in Axapta in Finance | Seth
2002-10-31 | B | 100 | Gap |  | Calendar to see the amount of callbacks for 3 days before and 3 days after scheduled callback and ability to change date from calendar
2002-10-31 | B | 101 | OMS |  | Add to work flow choice to request catalog on sales opportunity |  |  |  | Page 15 Sales Opportunity Management version 1.0
2002-10-31 | B | 102 | Gap |  | Ability to rollover past due callback. Keep original callback date |  |  |  | Leave up to individual rep
2002-10-31 | B | 103 | Decision |  | Should open callbacks be allowed on expired sales opportunity
2002-10-31 | B | 104 | OMS |  | Residential leads have 45 day ownership from date created |  |  |  | This needs to be added to OMS document
2002-10-31 | B | 105 | Gap |  | After lead is expired system should automatically re-assign based on round robin
2002-10-31 | B | 106 | Action |  | Provide new business rules | Seth |  |  | emailed to Erik 11/04/02
2002-10-31 | B | 107 | Security |  | What can be changed on business relationship table | Rebecca |  |  | When will rep be able to view, edit or make new
2002-10-31 | B | 108 | Gap |  | Ability to expire sales opportunity

## Nov. 5, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-11-05 | B | 109 | Gap |  | Pay commission based on the group that sales the item |  |  |  | for example: If equipment sales a part, they will not make as much commission if someone in sales sold the same part
2002-11-05 | B | 110 | Mod |  | Ability to adjust commissions based on finance approval percentage (CFC)
2002-11-05 | B | 111 | Issue |  | Track volume boards to apply to commissions
2002-11-05 | B | 112 | Issue |  | Misc adjustments of commissions |  |  |  | for example: RMA'S or referrals. When an item is returned the commission adjustment should be based on the original amount paid. Commission should be based on original ship date
2002-11-05 | B | 113 | Issue |  | Commission must total 100%
2002-11-05 | B | 114 | Issue |  | Ability to see commission on sales order at line level
2002-11-05 | B | 115 | Change |  | Ability to add addresses manually for distributors. Address should not be attached to customer account
2002-11-05 | B | 116 | Issue |  | Ability to verify an authorized buyer or caller, etc |  |  |  | Maybe incorporate support number. A unique number used for person to use to verify the person is authorized to call or purchase.
2002-11-05 | B | 117 | Issue |  | Ability to make a PO # mandatory for certain customers
2002-11-05 | B | 118 | Action |  | Give Erik a complete list of Business rules that will stop an order from being released | Team B |  |  | Get information to Brenda by 11/06/02
2002-11-05 | B | 119 | Action |  | What are the business rules to place a customer on hold | Brenda |  |  | Brenda will discuss with Marty
2002-11-05 | B | 120 | Action |  | Schedule a meeting to discuss price list | Ann Trainer
2002-11-05 | B | 121 | Issue |  | Ability to specify a price list per customer along with level (chairman, gold) also based on Product group
2002-11-05 | B | 122 | Issue |  | Ability to cancel sales order
2002-11-05 | B | 123 | Issue |  | Ability to view previous orders |  |  |  | View orders by group, date range, customer #, order #, etc

## Nov. 6,2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-11-06 | B | 124 | Issue |  | Ability to choose whether to ship orders with items on backorder |  |  |  | Products would like to ship a partial order without having sales manager's approval. Equipment will need sales manager's approval.
2002-11-06 | B | 125 | Issue |  | Ability to specify product terms based on product group (AG, SB) also based on customer number
2002-11-06 | B | 126 | Issue |  | Order validation to ensure the correct parts, lamps, beds are being ordered |  |  |  | for example, if customer is buying a lamp, provide a pop up window that verify that the lamps ordered will work in the bed that the customer owns. This should not be mandatory. Also based on customer group.
2002-11-06 | B | 127 | follow up |  | Discuss the number is customers that are classified as commercial that will need to use net terms | Mike Alonzi
2002-11-06 | B | 128 | Issue |  | Ability to accept payments through EFT |  |  |  | CIT uses this for the maintenance agreement. Move to Team E
2002-11-06 | B | 129 | Issue |  | Ability to set up a recurring order to charge credit card customers for CIT maintenance agreement |  |  |  | Currently CIT is entering the credit card payments manually for recurring orders
2002-11-06 | B | 130 | Definition |  | When can a reservation be made on an order. Can Net orders have different rules than prepaid for reserving items | [5 empty] | Y
2002-11-06 | B | 131 | Issue |  | The approval process for prepaid orders need to created
2002-11-06 | B | 132 | Discussion |  | Marty is going to have to look in two different places to approve orders | Mike Alonzi
2002-11-06 | B | 133 | Decision |  | How should print out of quotation or sales order look like | Mike Alonzi
2002-11-06 | B | 134 | Action |  | Determine all of the templates that are used and how should they look | Mike Alonzi/Erik Stromblad
2002-11-06 | B | 135 | Issue |  | Ship Sets |  |  |  | Ship sets are put on bed orders when more than one bed is placed on an order that should be shipped out at once.
2002-11-06 | B | 136 | Action |  | Create a model of predictive lamp replacement so that each equipment or lamp customer could be proactively contacted regarding lam replacements based on lamp usage | Mike Alonzi

## Nov. 11, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-11-11 | B | 1 | Cross Functional |  | Customer is only able to have one price list |  |  |  | Customer may have different price structures for different products that will require more than one price list
2002-11-11 | B | 2 | Cross Functional |  | Automatically move customer to next pricing level |  |  |  | once customer has purchased a certain dollar amount they are moved from chairman to gold chairman
2002-11-11 | B | 3 | Cross Functional | Scope | Show a running dollar amount of customer purchases to see if they qualify for next price list |  |  |  | need flexibility to show dollar amount and order quantity based on fiscal year
2002-11-11 | B | 4 | Action | Documentation | Provide different levels of pricing for customer per product line | John Keiffner | 2002-11-11 |  | Would like ability to see how far customer is away from moving to next pricing level.
2002-11-11 | B | 5 | Action | Documentation | Provide different levels of pricing for equipment customer | Wendy Schwartz | 2002-11-11
2002-11-11 | B | 6 | Action | Documentation | Provide Erik a list of all the promotions that have ran the past year | John Keiffner | 2002-11-11
2002-11-11 | B | 7 | Action | Documentation | Provide Erik a list of all the promotions that have ran the past year | Leslie Hartlieb | 2002-11-11
2002-11-11 | B | 8 | Issue | Scope | Ability to generate a coupon based on item sold |  |  |  | Example: if customer purchases a speed bed, the customer will get a coupon for $100 off speed lamps
2002-11-11 | B | 9 | Action | Documentation | Provide Erik a list of all the business rules that apply to pricing for all areas | Rebecca Cantrell | 2002-11-15

## Nov. 12, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-11-12 | B |  | Action | Admin | Get business rules for inventory reservations | Ann Trainer | 2002-11-15 |  | Should include sales and service. Also include rules for Finance orders and orders that have a future ship date
2002-11-12 | B |  | Action | Security | Who can change credit tolerances and who can release orders for shipment | Rebecca Cantrell
2002-11-12 | B |  | Gap | Requirement | Ability to put an order on hold on customer level and product level |  |  |  | Orders can still be placed for customer but must be manually approved. For example, warranty orders, etc.
2002-11-12 | B |  | Action | Admin | Provide RMA form | Karen Tackitt | 2002-11-12 | 2002-11-12 | Karen went over form line by line
2002-11-12 | B |  | Gap | Requirement | Need an interface to UPS to generate call tag |  |  |  | Give to Team E
2002-11-12 | B |  | Gap | Requirement | Do not show credit when RMA is received. |  |  |  | Axapta standard does not show a credit on customer's account when the merchandise is received back. Another step has to put credit on acct.
2002-11-12 | B |  | Gap | Requirement | Ability to charge customer misc fees on RMA's and reduce credit amount owed to customer |  |  |  | Customer may be responsible for freight charges or restocking fee. Credit amount should be less the charges
2002-11-12 | B |  | Action | Admin | Gather information on how the Transportation department processes an RMA | Ann Trainer | 2002-11-13 | 2002-11-13
2002-11-12 | B |  | Gap | Requirement | Interface truckline RMA's to generate call tag orders |  |  |  | Give to Team E
2002-11-12 | B |  | Action | Admin | Provide team with a copy of all forms and spreadsheets | Pauline Littlefield | 2002-11-15

## Nov. 13, 2002 (hidden)
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-11-13 | B |  | Gap | Requirement | Ability to readily see that an item is no longer under warranty or that warranty if voided
2002-11-13 | B |  | Gap | Requirement | Ability to have a suggestion box to cross check part or\dered or to suggest a part to order
2002-11-13 | B |  | Gap | Requirement | Ability to enter warrant information based on business rules for a particular product |  |  |  | Lamps and beds have a separate warranty from eachother. Also parts and different levels of warranties.
2002-11-13 | B |  | Action | Documentation | Provide Jen a list of all the warranty levels | Leslie | 2002-11-13
2002-11-13 | B |  | Gap | Requirement | Ability to attach warranty info to sales order via an order line
2002-11-13 | B |  | Gap | Requirement | Ability to track CIT Maintenance subscription |  |  |  | Some maintenance agreements are on a monthly draft (the customer is charged month) some are on a yearly draft. A draft is a payment. Track whether customer has maintenance subscription or not
2002-11-13 | B |  | Action | Admin | Erik will research to see if Axapta will allow call backs to be created based on the ship date of an order | Erik | 2002-11-15
2002-11-13 | B |  | Gap | Requirement | Ability for customers to have self-service inquiry capabiity |  |  |  | Per Erik, this is out of the scope for this project. Per Brenda it is in the scope for this project but may not go live Sept. 03
2002-11-13 | B |  | Action | Documentation | Get list of keywords to Erik | Rebecca | 2002-11-14
2002-11-13 | B |  | Decision | Security | Who will be able to assign activities | Rebecca
2002-11-13 | B |  | Action | Documentation | Define the business rules for callbacks | Wade | 2002-11-19 |  | includs types of callbacks. Time span between the time an activity is scheduled and the customer is called back
2002-11-13 | B |  | Action | Documentation | Define the business rules for notifying sales reps about current issues with sales opportunities | Seth | 2002-11-15 |  | If a customer has an issue and a service tech needs to resolve an issue, how should sales rep should be notified
2002-11-13 | B |  | Action | Requirement | Ability to download CIT customer database into a pda to use with after hours support helpdesk | Erik | 2002-11-14 |  | Erik is going to sit with Ryan 11/14/02 am and will determine if this is possible

## Nov. 14, 2002 (hidden)
ETS Issue Log | [7 empty] | Status | Description | Total
[8 empty] | 1 | Open | 14
[8 empty] | 2 | In Development - Aston | 0
[8 empty] | 3 | Resolved - Aston | 0
[8 empty] | 4 | In Test - ETS | 0
[8 empty] | 5 | Approved - ETS | 0
[8 empty] | 6 | Deferred | 0
[8 empty] | 7 | No Action | 0
Date
Open Date | Team/ Originator | Issue # | Type | Function | Issue Description | Assigned to | Due Date | Actual Date | Comment/Status | Status | Exec Decision
2002-11-14 | B | 169 | Action | Documentation | Charge backs of promotional items on commission | Mike Alonzi | 2002-11-18 |  | For example, a sales rep sales a bed for 2000 but a TV is given away for free that is worth $50. The commission paid to the rep is on the $2000 minus the cost of the promotional item. | 1 | N
2002-11-14 | B | 170 | Decision | Requirement | Can price list creation be centralized into one group instead of separate groups like it is today | Leslie | 2002-11-18 |  | Leslie provide Erik all of the price lists | 1 | Y
2002-11-14 | B | 171 | Gap | Requirement | Activity alert that the customer is eligible for a new discount price group |  |  |  |  | 1 | N
2002-11-14 | B | 172 | Gap | Requirement | Ability to mark an item as a non-discountable item or limit the discount amount |  |  |  | Sales reps are able to over-ride pricing on an order but some items should not have that ability or require a reason code and order must go through manager approval | 1 | N
2002-11-14 | B | 173 | Action | Admin | Put together a workflow of an order process | Mike Alonzi | 2002-11-18 |  |  | 1 | N
2002-11-14 | B | 174 | Gap | Requirement | Freight Quote alert |  |  |  | The computer automatically calculates freight if 3 or fewer beds are ordered, but the system requires a freight quote if 4 or more are ordered on the same line or with ship set | 1 | N
2002-11-14 | B | 175 | Gap | Requirement | Allow certain areas of an order to be changed without forcing recalculating of freight. But if something is changed that will change the freight amount, force the freight recalculation |  |  |  |  | 1 | N
2002-11-14 | B | 176 | Action | Documentation | Define how the system should prioritize red tag and blue tag orders | Ann Trainer | 2002-11-19 |  |  | 1 | N
2002-11-14 | B | 177 | Gap | Requirement | Ability to charge sales tax to freight |  |  |  |  | 1 | N
2002-11-14 | B | 178 | Gap | Requirement | Ability to indicate a separate freight carrier and delivery date per order line |  |  |  |  | 1 | N
2002-11-14 | B | 179 | Gap | Requirement | Ability to indicate a separate ship to address per order line |  |  |  |  | 1 | N
2002-11-14 | B | 180 | Gap | Requirement | Ability to build business rules that will only send certain orders to manager approval que |  |  |  |  | 1 | N
2002-11-14 | B | 181 | Action | Documentation | Define the business rules for inputting sales orders | Ann Trainer | 2002-11-22 |  | *Prospect *Sales Opportunity *Quotation *Sales Order *Sales Orderline *Activities | 1 | N
2002-11-14 | B | 182 | Action | Admin | Schedule a meeting to present business rules to Aston | Ann Trainer | 2002-11-20 |  |  | 1 | N
2002-11-14 | B | 183 | Action | Admin | Send out an email and ask for a list of business rules based on Iist in Iusse #181 | Ann Trainer | 2002-11-14
2002-11-14 | B | 184 | Action | Documentation | Define business rules for merging an account | Ann Trainer | 2002-11-20

## Issues Explanation
Action Log <Chapter>
Initiative
Issue No. | Team/ Originator | Registration Date | Priority | Issue Description | Assigned to | Due Date | Actual Date | Status | Comment/Status
1 | Enter Chapter name and Initiative where there are many initiatiives
2 | Enter Action information from Minutes, status report or any other source
Note on A3: : Assign a unique number to the Actioin.
Note on B3: : Where does the issue come from? Who has raised the Action?
Note on C3: : At what date was the a raised?
Note on D3: : L = Low M = Medium H = High
Note on E3: : Enter a short but telling description, what the action is about and what possible solutions are discuesssed
Note on F3: : Enter name of person responsible for solving action
Note on G3: : Enter date until when the action needs to be solved.
Note on H3: : Enter date when action was solved.
Note on I3: : R = Registered I = In discussion S = Solved