## Slide 1: Margins and Reserves for Performance Requirements of Systems with New Technologies
Lou Wheatcraft Wheatland Consulting, LLC
Copyright © 2020 by Wheatcraft. May only be used with permission

## Slide 2: Why is the management of margins and reserves such an issue?
In a talk by Gentry Lee, he tells a story where he was approached by a young engineer who asked him how it was possible for intelligent engineers to be off the mass by 50%.
Gentry replied that “engineers and scientists tend to be overly optimistic at the beginning of a project.”
There is often an over-reliance on technologies that are at a low maturity level – a low TRL.
  Because of this over-reliance, resource requirements are often defined that are “best case” or “theoretical” values based on approximations and assumptions for an “average or nominal” case.

## Slide 3: Impact of margins and reserves on project success
The failure to appreciate the need to define margins and reserves at the beginning of the project to mitigate the risk often results in cost and schedule overruns (due to the need to fix problems later in development) or failure of the system or product to meet stakeholder expectations in the operational environment (fail system validation).
“A good systems engineer appreciates and understands the need to manage resource margins and reserves.” Gentry Lee

## Slide 4: Margins defined
Development/technical margin: the difference between the estimated resource value defined at the beginning of project development activities and the actual amount of the resource value at the end of development when the system is delivered.
  Margins allow for both expected and unexpected change as the design matures over the system development lifecycle.
  Development margins for resources are defined at the system level and allocated to the parts of the system architecture.
Operational margin: the difference between what is required during operations and what is actually provided.
  Provides additional capability to address unexpected changes that may occur during operations.
  Can be used to mitigate variances in the hardware over time
  Can be used to mitigate variances in the quality of the assay
    Due to quality of the sample, reagents, preparation procedure

## Slide 5: Reserves & Resources Defined
“Management Reserve”: the portion of the available resource held back or kept “in reserve” by management or resource owner during development and not made available through allocation.
  Reserves allow management to deal with the unexpected such as out of-scope demands, unplanned changes, and other uncertainties during development.
“Resources”: are a quantity of a “thing” that is critical to successful planning, development, and operations of your system.
  For software resources could include CPU speed, cache memory, bandwidth, amount of data to be processed, storage, number of messages, number of commands over time, number of users, bandwidth, response time, reliability, availability, number of cycles, etc.
  For an Instrument resources could include performance, Total Allowable Error, time to do a test, accuracy, precision, quality (reliability, availability, other –ilities), lifetime, power (generation and usage), mass, size, acoustics, thermal, etc.)
  Some resources are are produced/achieved (performance, power, accuracy), some are consumed/used (time, power, mass, total allowable error, etc.)

## Slide 6: Allocation is more than just “flowing down” requirements from one level to another.
Two types of allocation:
  Allocation for responsibility
  Allocation of resources (performance, mass, power, consumables, -ilities, etc.)
Allocation of resources (budgeting)
  Need to be managed at the system level
    Dynamic activity – not static
    Useful to view allocation of resources as an equation of dependent variables
SE 1
Sys PW
SE 2
SE 3
Sys PW(t) = SE1(pw1) + SE2 (pw2) + SE3 (pw3)
SE = System Element
Sys PW(t) = Maximum power

## Slide 7: Equation form of allocation (budgeting)
Sys PW(t) = SE1(pw1) + SE2 (pw2) + SE3 (pw3)
SE 1
Sys PW
SE 11
SE 12
SE 13
SE 2
SE 21
SE 22
SE23
SE 3
SE 31
SE 32
SE 33
= SE11(pw11) + SE12 (pw12) + SE13(pw13)
= SE21(pw21) + SE22 (pw22) + SE23(pw23)
= SE31(pw31) + SE32 (pw32) + SE33(pw33)
Dependency
Need a way to manage budgets & dependencies!

## Slide 8: Resource Management
Resources at the system level need to be allocated (budgeted) to parts of the architecture
  Instrument, assay, software
This process repeats at each level
Budgeted amounts are often dependent variables in the overall resource equation
  The budgeted amounts will often change over the product life cycle.
  Need a way to manage changes to the budget amounts
The budgeted amounts are constraints
  Developers (inhouse and vendors) need to know these constraints

## Slide 9: Resource Management
To ensure consistency between the dependent requirements, they must be linked and managed as a set.
Key questions:
  Who does the Allocation?
  How are the budgets between parts determined?
    Estimates, models, WAGs?
    Initial computations are only approximations based on assumptions that may or may not be correct and may change as the system design matures
    Performance is often overestimated while consumption/usage is often underestimated
  How much confidence is there in these budgets?
    The lower the confidence, the higher the risk!
  How does the confidence change over time?
  How can the budgets be tracked and managed over the life of the project?
  How can changes to the budgets be managed between the different development teams (inhouse and vendors)?
Failure to address feasibility and properly assign values and manage change results in failed system verification and validation

## Slide 10: Resource Consumption Margins and Reserves
Expected growth in demand
Allowance for unexpected growth in demand
“Base Value”, also known as Current Best Estimate (CBE), is computed from the most recent design concepts for the current TRL.
Constrained by production

## Slide 11: Resource Production Margins and Reserves
Capability must be equal to or greater (positive gap) than the need
“Ceiling Value”, also known as Current Best Estimate (CBE), represents an assessment of the quantity of the resource the system should produce – theoretically.
Expected shortfall
Allowance for unexpected shortfall
Need is customer driven
Capability is technology driven

## Slide 12: Management notes:
Resource Production Requirements [1 & 2] and Resource Demand Requirement are constraints on the developer
  Defining margins and reserves are part of defining these requirements
Management of the margins is often very dynamic in the early stages of system development
  As the TRL level increases, the uncertainties in capability will decrease and the confidence in the system of interest being able to meet the Resource Production Requirement (1) will increase and the Production Shortfall Margin and Development Margin will be reduced.
  The numbers will begin to stabilize as the parts are procured and integrated.
For critical/essential requirements, progress can be tracked as leading indicators
  Higher risk requirements need closer attention and tracking
  For outsourced parts of the architecture need to make sure provisions are included in the SOW to manage these types of requirements
    For RFPs and Proposal evaluation, you also need to address the ability of the vendor to meet these requirements. (Can ask for what margins they are including)
Feasibility and technology maturity (TRL) must be addressed early in the project as part of concept maturation and needs definition

## Slide 13: How Big Should Margins and Reserves Be?
What you going to base the size of their resource margins and reserves?
  Minor updates to an existing system
  Average or generic product
  New product pushing state-of-the-art
Example (NASA mass margins – average/generic project)
  %Growth Allowance Margin + % Development Margin
    25-40% at scope baseline
    20-25% at Systems Requirements Review (SRR)
    15%-20% at Preliminary Design Review (PDR),
    15% at Critical Design Review (CDR),
    5%-10% at Test Readiness Review (TRR) – start of system verification
  For minor updates to an existing system, the margins could be even lower.
  For state-of-the-art the margins may need to be 5-10% higher

## Slide 14: How Big Should Margins and Reserves Be?
Gentry Lee recommends you base them on the answers to the following questions, and, based on the answer, define your resource margins and reserves accordingly:
  “How many things are being done for the first time?
  “How many things have been done once, but in a slightly different application in a slightly different operational environment?”
  “How many things being done have been done before in the exactly in the same manner and in the same operational environment?”
If everything falls into the last category, the risk is low (high TRL) and the use of average or generic margins are probably safe to use.
However, if much of the system falls into the first or second categories, the risk is much higher (low TRL)
  Margins and reserves at the beginning of the project need to be much larger (>50%).

## Slide 15: Discussion?