## ToC Info
Table of Content Sections | Contributions | Input Date/Status | Integrated to Master (Kevin Task) | 2/11/20 Comments | Considerations | Some sources of information
1 Introduction | Kevin Orr | Complete | Complete
1.1 Purpose and Scope (includes Problem Domain) | Kevin Orr | Complete | Complete
1.2 Audience | Kevin Orr | Complete | Complete | Set up like the Use cases, using example from INCOSE HB presentation
1.3 Approach | Kevin Orr | Complete | Complete
1.4 Definitions | In NRLC handbook |  |  |  | Use/consistent with industry standards
1.4.1 Requirement | In NRLC handbook
1.4.2 Requirements Development | In NRLC handbook
1.4.3 Requirements Management | In NRLC handbook
1.4 Guide Organization | Kevin Orr | Complete | Complete
2 Requirements Development and Management Context | Team
2.1 Requirement Handbooks/Standards | Go up one/two levels, not much detial here |  |  |  | Don M to help with trace between standards to GDMR
2.1.1 INCOSE SE Handbook | Team
2.1.2 IEEE 15288 | Team
2.1.3 Needs and Requirements Life-Cycle Management Handbook | Team
2.2 Differences between Requirements Develpoment and Requirements Management (RM is not a process in INCOSE SE HB) | In NRLC handbook
3 Needs Development | Celeste Drewien | Complete | 2020-03-27
3.1 I/O Overview | Celeste Drewien | Complete | 2020-03-27
3.2 Identify Source/Stakeholders | Celeste Drewien | Complete | 2020-03-27
3.3 Needs Definition (Stakeholder elicitation) | Celeste Drewien | Complete | 2020-03-27
3.4 Needs Analysis (including unknowns TBx) | Celeste Drewien/Tami K | Complete | 2020-03-27 | Tami writing on TBx (2/28/20)
3.5 Needs Verification and Validation | Celeste Drewien | Complete | 2020-03-27 | Consider using checklist similar to as Req V&V
3.6 Gate Review (Internal??/Extenal??) | Celeste Drewien | Complete | 2020-03-27
4 Requirements Development | Ron Carson | Complete | 2020-03-27 |  | Need to ensure to include needs as well as requirements
4.1 I/O Overview | Ron Carson | Complete | 2020-03-13 |  | - Provide common stages of requirement development during a product lifecycle - Address the iterative nature of working requirement development - Address impacts of design and modeling to inform the maturation of the requirement set - Address concepts (and warnings) of using requirements from similar projects to assist in requirement set development and other guidance for efficient approaches - incluses the process | - Requirement development trends among requirement development, design development, requirement development, design development path, less of a waterfall and more of a sandwich that combines requirements, models and design (2004 Dick Chard INCOSE paper) - Key approaches for implementing requirement development (2010 Wheatcraft Constellation INCOSE paper)
4.2 Requirement Sources | Ron Carson | Complete | 2020-03-13
4.2.1 Stakeholder Needs | Ron Carson | Complete | 2020-03-13
4.2.2 Analysis | Ron Carson | Complete | 2020-03-13 |  | - Describe types and common sources of various requirement types (functional/performance, design, environmental, and “ilities”) - Provide guidance on approaches to apply these to the requirement set
4.2.3 Architecture/Models | Ron Carson | Complete | 2020-03-13 |  | - Expand on research on usage of models during the requirement development process - Tie into MBSE efforts and how it informs requirement development
4.3 System Requirement Set | Tami Katz | Complete | 2020-03-20
4.3.1 Minimum Set of Requirement Attributes and data schema | Pointer to GFWR/Kevin | Complete | 2020-03-20 |  |  | Guide for Writing Requirements
4.3.2 Traceability | Tami Katz | Complete | 2020-03-20 |  | -Provide guidance on requirement trace matrices - Provide overview of requirement sources and address trace to parent and trace to source from Guide for Writing Requirements (guidance on addressing lower requirements based on industry practices, regulations, nonfunctional needs)
4.3.3 Requirement Validation and Verification | Henrik Mattfolk | Complete | 2020-03-20 | Researching, seeing good input from the manual, could summarize manual information into a checklist (one for Req Verif, and one for Req Validation) May find some info in the summary of GfWR | - Address validation of the requirements set based on Guide for Writing Requirements Sect 3 - Provide process for requirement V&V (part of requirement management effort), with interface to Guide for V&V - Provide best practices to ensure requirement set supports overall V&V, with interface to Guide for V&V - Might consider leaving validation here and move verification to RM - Bring in Requirement V&V from V&V guide
5 Needs and Requirements Management | Rick Hefner | 2020-03-20 | 2020-03-20
5.1 I/O Overview | Rick Hefner | 2020-03-20 | 2020-03-20 |  | - Provide common stages of requirement management during a product lifecycle - Address the iterative nature of working requirement management - Address impacts of design and modeling to inform the maturation of the requirement set - Model based compared to formal configuration management requirement documentation - Considerations of supplier contract needs - Addressing management of a requirement set that addresses multi use, multiple customers of a product line, and evolution of a product
5.2 Requirements Baseline Process | Henrik Mattfolk | Complete | 2020-03-20
5.3 Requirements Change Process | Henrik Mattfolk | Complete, suggest reference RMP templlate appendix | 2020-03-20 |  | - Provide guidance on processes to change requirements and considerations when assessing impacts
5.3.1 Feedback loop from System/Design V&V-Requirement reviews | Henrik Mattfolk | Complete | 2020-03-20
5.3.2 Configuration Management of Requirements | Henrik Mattfolk | Complete | 2020-03-20
5.4 Attributes for Requirements Management | Pointer to GFWR/Kevin | Complete | 2020-03-20 |  |  | Guide for Writing Requirements
6 Considerations on Tools and Data Exchanges | Pointer to Integrated Data white Paper |  | 2020-03-20 |  | - Address need for data connectivity (data integration paper) - Address options for consideration of the various tools based on project needs and resources - Provide guidance on some best practices | Tool selection should be aligned with having an integrated data set (2017 Wheatcraft INCOSE paper)
Appendix A - Acroymns | Kevin Orr |  | 2020-03-27
Appendix B - Requirements Management Plan Template | Rick Zinni | 2020-03-23 | 2020-03-27 | Draft
Appendix C - Uniqueness across Industries | Step 1: List of domains to consider (Consumer products (appliances, electronics, etc) , Automotive, Oil &Gas, Medical Devices, Gov't Contracting (Aero, NASA, DoD,), Commercial products (aircraft, satalite, etc), Step 2: Product Lines/scale (small, med, large) | 2020-03-20 | 2020-03-27 | Consider separtation by product line (system, Component, etc) (Coordination with Product Line WG) Consider separation by Industry (Coordinate with other domain WG automotive, O&G, etc) | Users and Uses Case similar to SE HB Presentation
Appendix E - Attributes
Appendix D - Case Study – Coffee Machine | Might be separate case study document | Phase II
Appendix E - Comment Form | NA
Key
Section Input Provided | 54.29%
Section Integrated into master
Draft 1 Synced with Manual

## ToC Traceability
GDMR Draft (Oct 2020) | NRLM (Version 30 Sep 2020) | INCOSE HB (v?? Date)
1 Introduction
1.1 Purpose and Scope (includes Problem Domain) | 1.1 Purpose and scope
1.2 Audience | 1.2 Audience
1.3 Approach | 1.3 Approach
1.4 Definitions | 1.4 Needs and Requirements Development and Management 2.2 Definitions
1.5 Guide Organization | 1.5 Needs and Requirements Lifecycle Manual Organization
2 Needs Development, Verification, and Validation | Section 4: STAKEHOLDER NEEDS DEFINITION PROCESS
2.1 Stakeholder Needs Definition Activities | Section 4: STAKEHOLDER NEEDS DEFINITION PROCESS
2.1.1 Plan for Stakeholder Needs Definition | 4.1 Plan for Stakeholder Needs Definition
2.2 Define Inputs to Lifecycle Concepts Analysis and Maturation | 4.2 Define Inputs to Lifecycle Concepts Analysis and Maturation
Steps 1 and 2 | 4.2.1 Define the Problem, Threat, or Opportunity 4.2.2 Define Mission, Goals, Objectives, and Measures of Suitability
Step 3 | 4.2.3 Identify External and Internal Stakeholders
Step 4 | 4.2.4 Elicit Stakeholder Needs and Requirements
Step 5 | 4.2.5 Document Elicitation Outcomes
Step 6 | 4.2.6 Identify Drivers and Constraints
Step 7 | 4.2.7 Identify, Assess, and Handle Risks
2.2 Needs Sources/Stakeholders
2.2.1 Identify Stakeholder | 4.2.3 Identify External and Internal Stakeholders
2.2.1.1 Stakeholder Roles
2.2.1.2 Concepts Discussion and Bounding the Problem with Key Stakeholders
2.2.2 Stakeholder Over the System Life Cycle
2.2.3 Priority of Stakeholders
2.2.4 Stakeholder Communications
2.3 Needs Definition (Stakeholder elicitation)
2.3.1 Need Statement
2.3.2 Need Expression
2.3.3 Need Set
2.3.4 Needs Elicitation | 4.2.4 Elicit Stakeholder Needs and Requirements | 4.2.2 Elaboration 4.2.2.2 Elicit Stakeholder Needs
2.3.4.1 Elicitation Process | 4.2.4.1 Plan for Elicitation
2.3.4.2 Elicitation Techniques and Methods | 4.2.4.2 Elicitation Techniques and Methods
2.3.4.3 Needs Collection and Elicitation
2.4 Needs Analysis (including unknowns TBx)
2.4.1 Developing a Need Within the Control of the SE Team
2.4.2 Clarifying Needs
2.4.3 Resolving Needs Amongst Various Stakeholders
2.4.4 Analyzing Needs for Vailidity
2.4.5 Recording and Managing Needs
2.4.6 Prioritizing Needs
2.4.7 Managing Unknowns During the Needs and Requirements Develpoment Process | 4.5.2.6 Managing Unknowns
2.5 Needs Verification and Validation
2.5.1 Definitions
2.5.2 Needs Verficaiton Process | 5.1 Stakeholder Needs verification Process
2.5.3 Needs Validation Process | 5.2 Stakeholder Needs Validation Process
2.6 Needs Gate Review (Internal/External)
3 Requirements Development
3.1 I/O Overview Or Lifecycle of Requirements Development
3.1.1 Gathering Needs: "Requirement Elicitation" |  | 4.1 and 4.2
3.2.1 Analysis, Refinment, Translation into Requirements |  | 4.3
3.1.3 Validation with Stakeholders: Necessity, Sufficiency, Verfiability, Feasibility |  | 4.3
3.1.4 Design/Architecture Implementation: Feasibility, Feedback and Recursion |  | 4.3, 4.4, and 4.5
3.1.5 Verification: Satisfaction of Requirements |  | 4.9
3.1.6 Validation: Satification of Needs |  | 4.11
3.1.7 Support: Changes Over Time During Operations
3.2 Requirement Sources
3.2.1 Stakeholder Needs |  | 4.1 and 4.2
3.2.2 Requirement Analysis |  | 4.3
3.2.2.1 Requirement Types
3.2.2.2 Application to Analysis
3.2.2.3 Completeness
3.2.3 Architecture/Models |  | 4.3 and 4.4
3.3 System Requirement Set
3.3.1 Minimum Set of Requirement Attributes and data schema
3.3.2 Traceability | 6.2.2.3 Establishing Traceability between Children Requirements and the Allocated Parent or Source
3.3.3 Requirement Validation and Verification
3.3.3.1 Requirement Validation Developmetn
3.3.3.2 Requirement Verification Development
3.4 Sumamry of Requirements Development
5 Needs and Requirements Management
5.1 I/O Overview
5.2 Requirements Baseline Process
5.3 Requirements Change Process
5.3.1 Feedback loop from System/Design V&V-Requirement reviews
5.3.2 Configuration Management of Requirements
5.4 Attributes for Requirements Management

## Schedule
Tasks | GDMR Date | GVV Tasks | GVV Date | NRLCM Tasks | NRLCM Date
Update TPP? | IW 2020 | Update TPP? | IW 2020 | Create & submit new online TPP | 2020-03-01
Confirm ToC and writing assignments | IW 2020 | Confirm ToC and writing assignments | IW 2020 | Incorporate old GtVV IW2020 reviewer comments & combine drafts of old GDMR & GtVV, add rest of content –> Draft 1 | 2020-02-01
Contributor inputs | IW2020 thru February 28, 2020 | Contributor inputs | IW2020 thru March 6 | Alignment with INCOSE SE HB/15288 | 2020-03-01
Virtual Meeting: Contributors (Status/help needed on content) | 2/11/2020 @ 1pm Central for 1.5hr | Virtual Meeting: Contributors (Status/help needed on content) | Mid Feb., others | Send Draft1 out for first review and comment | April 2020 (3-week review)
Integrate Inputs | February 29, 2020 thru March 31, 2020 | Integrate Inputs | March 7 – March 31 | Integrate Review1 comments –> Draft 2 | 2020-05-01
Virtual Meeting: Contributors (Status/comments on inputs) | 2020-03-13 |  |  | Editorial committee meeting to address issues and provide status | May ?, 2020
Contributor/Editorial committee Review (NRLCM Draft 1 sync point) | April 1, 2020 thru April 30, 2020 | Contributor/Editorial committee Review (NRLCM Draft 1 sync point) | April 1, 2020 thru April 30, 2020 | Integrate editorial committee comments –> Draft 3 | June ? - ?, 2020
Virtual Meeting: Contributors/Editorial Committee (Status) | 2020-04-15 |  |  | Send Draft3 out for review and comment | July 2020 (3-week review)
Integrate Comments | May 1, 2020 thru May 28, 2020 | Integrate Comments | May | Integrate review2 comments –> Draft 4 | 2020-08-01
Virtual Meeting: Contributors/Editorial Committee (Status) | 2020-05-19 |  |  | Editorial committee meeting to address issues and provide status | August ?, 2020
GDMR Review Team review (NRLCM Draft 2 sync point) | May 29, 2020 thru Jun 26, 2020 | G to V&V Review (NRLCM Draft 2 sync point) | Late May / Early June | Integrate editorial committee comments –> Prototype | September ? - ?, 2020
Disposition/Integrate Comments from GDMR Review Team | June 27, 2020 thru July 17, 2020 | Disposition/Integrate Comments from G to V&V Review Team | Early July
RWG (IS2020) Review (NRLCM Draft 3 sync point) | July 24, 2020 thru August 28, 2020 | RWG (IS2020) Review (NRLCM Draft 3 sync point) | Mid July – through end of Aug
Disposition and Incorporate RWG Comments | August 15, 2020 thru September 4, 2020 | Disposition and Incorporate RWG Comments | September
Virtual Meeting: Contributors/Editorial Committee (Status) | 2020-08-26
Submit to Tech Ops for final Release | 2020-09-14 | Submit to Tech Ops for final Release | Early October | Prototype 1 sent to IPC for review | Oct 1, 2020 (7-8 week review)
Virtual Meeting: Contributors/Editorial Committee (Final Updates) | 2020-10-21 |  |  | Receive IPC Prototype comments | 2020-12-01
Final GDMR Submitted | 2020-12-01 | Final G to V&V Submitted | 2020-12-01 | Incorporate IPC prototype review comments -> Final Document | 2020-12-01
Announcement/Release of GDMR | IW2021 | Announcement/Release of G to V&V | IW2021 | Send IPC Review comments disposition and Final Document to IPC for Approval | Early January 2021
|  |  |  | Final IPC document approval and preparation for release completed per processes in TPP Tec-Proc-02. | January – February 2021
|  |  |  | Product published & released | 2021-03-01

## PoCs
First Name | Last Name | Email | Company | Role | Section | Confirmed | Notes
Kevin | Orr | txorrhome@gmail.com | Eaton | Contributor |  | Yes
Lou | Wheatcraft | louw@reqexperts.com | Requirement Experts | Contributor | Coffee Example | Yes
Ron | Carson | ronald.s.carson@gmail.com | Seattle Pacific University | Contributor | Requirement Development | Yes
Mike | Ryan | m.ryan@adfa.edu.au |  | Contributor |  | Yes
Rick | Zinni | rzinni@gmail.com |  | Contributor |  | Yes
Kathy | Baska |  |  | ??Contributor??
Tami | Katz | tami.katz@sncorp.com familykatz@earthlink.net |  | Contributor | 3.4, with focus on 3.4.2 Traceabiliey (functional and non-functional) | Yes
Susan | Ronning | susan@ebe-consulting.com | EBE Consulting | Contributor | Requirement Development | Yes
Raymond | Wolfgang | rwolfga@sandia.gov | Sandia National Labs | ??Contributor??
Basem | Fallatah | 7sbdest@gmail.com |  | Peer Review |  |  | From Orginal TPP
Douglas | Crocker | douglas.crocker@intel.com |  | Peer Review |  |  | From Orginal TPP
Elena | Gallego | elena.gallego@reusecompany.com |  | Peer Review |  |  | From Orginal TPP
Glenn | Meinhardt, Ph.D | glenn.meinhardt@gm.com | GM | Peer Review |  |  | From Orginal TPP
Hasan | Orten | hasanorten@gmail.com |  | Peer Review |  |  | From Orginal TPP
Jose | Fernandez | joselfernandez@telefonica.net | University of Madrid | Peer Review |  | Yes | From Orginal TPP
Kirill | Gaydamaka | k.gaydamaka@gmail.com | Irkut | Peer Review |  |  | From Orginal TPP
Mark | Ragon | markragon@att.net | Boeing | Peer Review |  |  | From Orginal TPP
Rick | Hefner | rhefner@caltech.edu | Caltech | Peer Review | 3.4.3 Requirement Verification and Validation | Yes | Also volunteered to assist with 3.4.3 if needed
Bob | Noel | robert.noel@boeing.com | Boeing | Peer Review |  |  | From Orginal TPP
Rummana | Sadiq | rsadiq@gnresound.com | GN Resound | Peer Review |  | Yes | From Orginal TPP
Tim | Kerby | tim@edinburgh.systems | Edinburgh | Peer Review |  |  | From Orginal TPP
Brian | Berenbach | brian.berenbach@gatech.edu bberenbach@alumni.emory.edu | Professional Education Georgia Institute of Technology | ?? |  |  | Provided a cheat sheet, no specifics on participating
Celeste | Drewien | cadrewi@sandia.gov | Sandia National Labs | Contributor |  | Yes
Henrik | Mattfolk | henrik_mattfolk@whirlpool.com | Whirlpool | Contributor |  | Yes
Wang | Zen | zywang@terrapower.com | Terra Power | ??
Simone | Bergand | simone.bergamo@edf.f | EDF | ??
Luis | Alonso | Luis.Alonso@reuse.compnay.com | The Reuse Compnay | ??
Trish | Briscue | plbrisc@sandia.gov | Sandia National Labs | Peer Review |  | Yes
Anthony | Desmond | anthony.t.desmond.civ@mail.mil | US Army ASA | ??
Mike | Gehringer | michael.d.gehringer@boeing.com | Boeing | ??Contributor??
Gordon | Woods | gordon.woods@hotmail.co.uk |  | Contributor | 5 Considerations on Tools and Data Exchanges | Yes
Donald | McNally | Donald.Mcnally@woodward.com | Woodward | Contributor |  | Yes
Bearden | Bill (Willliam) | wbearden1346@gmail.com |  | Peer Review |  | Yes | at IW2020
Fatherley | Quinn | fatherley4@llnl.gov |  | Peer Review |  | Yes | at IW2020
Garcia | Emmanuelle | emmanuelle.garcia@airbus.com | Airbus | Peer Review |  | Yes | at IW2020

## Actions_Comments
Description | Actionee | Source of Action | Notes | ECD | Closure Description
Consider dividing GDMR into two guides one for Development and one for Management |  | IS 2019 | Under consideration, will determine as GDMR is developed
Create Architecture of Guides |  | IS 2019
Guides can be linked across each other, contact Bill Chown for details
Updates to GDMR TPP: Add milestone to integrate with other guides Change IS to IW on milestone 7 Add milestone at beginning to have contributers sign IP release | Kevin Orr | IS 2019 |  | Done | TPP was sent to Tech Ops on ??
Look at WG completeness paper to ensure compliance | Kevin Orr | IS 2019
Need to consider activity and review with other working groups MBSE, O&G, Automotive, SE Tools, etc |  | GDMR meeting 10/11/19

## GDMROutline
From Kevin (Presented at IW 2019) | From Tami | From Ron
1. Introduction | Purpose of requirement development and management activities | Purpose
Purpose and Scope | General introduction | Process context and requirements: 15288/SE Handbook, CMMI
Problem Domain | Broad guidance of considerations, lessons learned | Requirements development
Audience | Lifecycle of the requirement development process | Lifecycle of RD
Approach | Provide common stages of requirement development during a product lifecycle | Using MBSE for requirements development; connection to other processes (e.g., Analysis, Architecture)
Definitions | Address the iterative nature of working requirement development | Non-functional requirements (connection to stakeholder Conops, MOEs and concerns in process 4.2)
Requirement | Address impacts of design and modeling to inform the maturation of the requirement set | Tools, including data exchange and standards
Requirements Development | Address concepts (and warnings) of using requirements from similar projects to assist in requirement set development and other guidance for efficient approaches | Handoff to Writing Requirements
Requirements Management | Considerations of requirement development using models | Validating Requirements (4.11)
Guide Organization | Expand on research on usage of models during the requirement development process | Handoff to Verifying systems
Requirements Development and Management Overview | Tie into MBSE efforts and how it informs requirement development | Traceability: at the intersection between requirements definition and management
Summarize Req Definition from INCOSE Handbook | Roles and responsibilities in requirement management | Configuration management of requirements: requirements management
SE Process | Describe typical roles on a project for implementation of requirement development and management | Life cycle of REQM
Project Lifecycle | Expand on constellation lessons learned from Lou Wheatcraft | Using MBSE for REQM (including variant and product line management)
Roles and Responsibilities | Management and assessment of a complete requirement set | Establishing CM attributes (handoff to “writing” and IV&V Guides)
Define Roles and Responsibilities | Address validation of the requirements set based on Guide for Writing Requirements Sect 3 | Tools, including data exchange and standards
Swimlane process chart (workflows and activities) | Provide guidance on requirement trace matrices
Requirements Development | Provide overview of requirement sources and address trace to parent and trace to source from Guide for Writing Requirements (guidance on addressing lower requirements based on industry practices, regulations, nonfunctional needs)
Requirement Gathering Process | Considerations on Tool Selection
Requirement Elicitation/Identification (Scope/Definition) | Address need for data connectivity (data integration paper)
Requirement Analysis | Address options for consideration of the various tools based on project needs and resources
Requirement Leveling | Provide guidance on some best practices
Requirement Network/Hierarchy | Guidance for generation of formal documentation
Minimum Set of Requirement Attributes and data schema | Model based compared to formal configuration management requirement documentation
Requirement Traceability | Considerations of supplier contract needs
Requirement Baseline | Options for the development of nonfunctional requirements
Requirement outputs | Describe types and common sources of nonfunctional requirements
Requirements artifact organization/reports (IEEE std, MIL STD) | Provide guidance on approaches to apply these to the requirement set
Tailoring process | Options for requirements in product line and products with multi-use lifecycles
Requirements Management | Addressing management of a requirement set that addresses multi use, multiple customers of a product line, and evolution of a product
Config/Change Control | Guidance for requirement change process
Deliverables/Expectations | Address requirement baseline and configuration management
Requirements Management Plan | Provide guidance on processes to change requirements and considerations when assessing impacts
Requirement Set | Addressing the need for requirement verification and validation
Tools | Provide process for requirement V&V (part of requirement management effort), with interface to Guide for V&V
Standard MS Office Toolset | Establishing a requirement process that enables product verification and validation
Requirement Management Databases | Provide best practices to ensure requirement set supports overall V&V, with interface to Guide for V&V
MBSE
Appendix A
Requirements Management Plan Template
Case Study – Coffee Machine

## Links to SourcesTitle
Title (hyperlink also) | Topic
Dick, J. and J. Chard, “The Systems Engineering Sandwich: Combining Requirements, Models and Design”, INCOSE International Symposium IS2004, July 2004. | Requirement Development
2010 Wheatcraft Constellation INCOSE paper | Requirement Development
2017 Wheatcraft INCOSE paper | Tools
Guide for Writing Requirements | Requirement Development Requirements Management
Wheatcraft, L., Ryan, M., Dick, J. “On the Use of Attributes to Manage Requirements”, Systems Engineering Journal, Volume 19, Issue 5, September 2016, pp. 448–458. | Requirement Development Requirements Management
INCOSE SE Handbook v4
NASA SE Handbook